## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Total | 35.5 days | October 26, 2022 8:00 AM | December 14, 2022 12:00 PM |  | 1
2 | Yes | Auto Scheduled | Implementations | 30.5 days | October 26, 2022 8:00 AM | December 7, 2022 12:00 PM |  | 2
3 | Yes | Auto Scheduled | Build users DB | 34 hrs | October 26, 2022 8:00 AM | November 1, 2022 10:00 AM |  | 3
4 | Yes | Auto Scheduled | Student | 16.75 days | October 28, 2022 8:00 AM | November 21, 2022 3:00 PM |  | 3
5 | Yes | Auto Scheduled | Build students DB | 20 hrs | November 1, 2022 10:00 AM | November 3, 2022 3:00 PM | 3 | 4
6 | Yes | Auto Scheduled | Build subjects DB | 10 hrs | October 28, 2022 8:00 AM | October 31, 2022 10:00 AM |  | 4
7 | Yes | Auto Scheduled | Allow student to choose subjects of interest | 16 hrs | November 14, 2022 8:00 AM | November 15, 2022 5:00 PM | 5,6 | 4
8 | Yes | Auto Scheduled | Allow student to add detailed information (ID, school, grade, etc.) | 16 hrs | November 17, 2022 3:00 PM | November 21, 2022 3:00 PM | 5,6 | 4
9 | Yes | Auto Scheduled | Teacher | 24.25 days | October 28, 2022 8:00 AM | December 1, 2022 10:00 AM |  | 3
10 | Yes | Auto Scheduled | Build teachers DB | 20 hrs | November 1, 2022 10:00 AM | November 3, 2022 3:00 PM | 3 | 4
11 | Yes | Auto Scheduled | Allow teacher to add basic personal information | 8 hrs | November 3, 2022 3:00 PM | November 4, 2022 3:00 PM | 10 | 4
12 | Yes | Manually Scheduled | Allow teacher to add expertise | 8 hrs | October 28, 2022 8:00 AM | October 28, 2022 5:00 PM | 6,10 | 4
13 | Yes | Auto Scheduled | Allow teacher to set a base pricings (daily, weekly, etc.) | 4 hrs | November 9, 2022 3:00 PM | November 10, 2022 10:00 AM | 11,12 | 4
14 | Yes | Auto Scheduled | Allow teacher to submit the profile for reviewing by admins | 8 hrs | November 10, 2022 10:00 AM | November 11, 2022 10:00 AM | 11,12,13 | 4
15 | Yes | Auto Scheduled | Show teacher's reviews in their profile | 10 hrs | November 30, 2022 8:00 AM | December 1, 2022 10:00 AM | 20 | 4
16 | Yes | Auto Scheduled | Show feedbacks from students privately | 12 hrs | November 18, 2022 8:00 AM | November 28, 2022 10:00 AM | 21 | 4
17 | Yes | Auto Scheduled | Teacher - Student interactions | 15.25 days | November 3, 2022 3:00 PM | November 24, 2022 5:00 PM |  | 3
18 | Yes | Auto Scheduled | Recommend suitable teachers to students | 32 hrs | November 21, 2022 8:00 AM | November 24, 2022 5:00 PM | 10,5,6 | 4
19 | Yes | Auto Scheduled | Search for teachers based on subject, teachers’ location, suitable teaching date, level (fundamental, advanced, …) | 28 hrs | November 3, 2022 3:00 PM | November 10, 2022 10:00 AM | 5,6,10 | 4
20 | Yes | Auto Scheduled | Can leave ratings & reviews after learning | 16 hrs | November 8, 2022 3:00 PM | November 15, 2022 5:00 PM | 5,10 | 4
21 | Yes | Auto Scheduled | Can leave feedback to teachers (anonimity is optional) | 16 hrs | November 14, 2022 10:00 AM | November 16, 2022 5:00 PM | 5,10 | 4
22 | Yes | Auto Scheduled | Communication system | 17 days | November 3, 2022 3:00 PM | November 28, 2022 3:00 PM |  | 3
23 | Yes | Auto Scheduled | Chatbox | 80 hrs | November 4, 2022 3:00 PM | November 28, 2022 3:00 PM | 5,10 | 4
24 | Yes | Auto Scheduled | Voice/Video call | 80 hrs | November 3, 2022 3:00 PM | November 17, 2022 3:00 PM | 5,10 | 4
25 | Yes | Auto Scheduled | Phone number (basic contact method) | 8 hrs | November 17, 2022 10:00 AM | November 18, 2022 10:00 AM | 5,10 | 4
26 | Yes | Auto Scheduled | Integrate with payment methods | 24 hrs | November 3, 2022 3:00 PM | November 8, 2022 3:00 PM | 5,10 | 4
27 | Yes | Auto Scheduled | Customer service | 20.25 days | November 7, 2022 8:00 AM | December 5, 2022 10:00 AM |  | 3
28 | Yes | Auto Scheduled | Build customer service DB | 16 hrs | November 7, 2022 8:00 AM | November 8, 2022 5:00 PM | 3 | 4
29 | Yes | Auto Scheduled | Answer support message | 16 hrs | November 28, 2022 3:00 PM | December 5, 2022 10:00 AM | 23,28 | 4
30 | Yes | Auto Scheduled | Answer hotline calls (aka. Urgent contact) | 8 hrs | November 9, 2022 8:00 AM | November 9, 2022 5:00 PM | 28 | 4
31 | Yes | Auto Scheduled | Admin | 18.25 days | November 11, 2022 10:00 AM | December 7, 2022 12:00 PM |  | 3
32 | Yes | Auto Scheduled | Allow tracking of chat messages | 12 hrs | November 28, 2022 3:00 PM | November 30, 2022 10:00 AM | 23 | 4
33 | Yes | Auto Scheduled | Allow tracking of reviews | 24 hrs | November 29, 2022 8:00 AM | December 7, 2022 12:00 PM | 20 | 4
34 | Yes | Auto Scheduled | Allow tracking of feedbacks | 24 hrs | November 21, 2022 8:00 AM | November 25, 2022 5:00 PM | 21 | 4
35 | Yes | Auto Scheduled | Allow manual user banning | 12 hrs | November 21, 2022 8:00 AM | November 22, 2022 12:00 PM | 3 | 4
36 | Yes | Auto Scheduled | Allow to approve/deny teachers' profiles | 6 hrs | November 11, 2022 10:00 AM | November 11, 2022 5:00 PM | 14 | 4
37 | Yes | Auto Scheduled | Testing | 5 days | December 7, 2022 1:00 PM | December 14, 2022 12:00 PM |  | 2
38 | Yes | Auto Scheduled | User testing | 24 hrs | December 7, 2022 1:00 PM | December 12, 2022 12:00 PM | 2 | 3
39 | Yes | Auto Scheduled | Smoke testing | 8 hrs | December 7, 2022 1:00 PM | December 8, 2022 12:00 PM | 2 | 3
40 | Yes | Auto Scheduled | System testing | 40 hrs | December 7, 2022 1:00 PM | December 14, 2022 12:00 PM | 2 | 3
41 | Yes | Auto Scheduled | Stress test | 24 hrs | December 7, 2022 1:00 PM | December 12, 2022 12:00 PM | 2 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Lương Duy Hưng | Hưng | Work |  |  |  |  | 100% | $20.00/h | 0
2 | Lương Quang Khánh | Khánh | Work |  |  |  |  | 100% | $20.00/h | 0
3 | Nguyễn Quý Hải | Hải | Work |  |  |  |  | 100% | $20.00/h | 0
4 | Trần Quốc Việt | Việt | Work |  |  |  |  | 100% | $20.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Build users DB | Nguyễn Quý Hải | 1 | 24h | 100%
Build users DB | Lương Duy Hưng | 1 | 24h | 100%
Build users DB | Lương Quang Khánh | 1 | 24h | 100%
Build users DB | Trần Quốc Việt | 1 | 24h | 100%
Build students DB | Trần Quốc Việt | 1 | 20h | 100%
Build subjects DB | Lương Duy Hưng | 1 | 10h | 100%
Allow student to choose subjects of interest | Nguyễn Quý Hải | 1 | 16h | 100%
Allow student to add detailed information (ID, school, grade, etc.) | Lương Duy Hưng | 1 | 16h | 100%
Build teachers DB | Lương Quang Khánh | 1 | 20h | 100%
Allow teacher to add basic personal information | Lương Quang Khánh | 1 | 8h | 100%
Allow teacher to add expertise | Nguyễn Quý Hải | 1 | 8h | 100%
Allow teacher to set a base pricings (daily, weekly, etc.) | Trần Quốc Việt | 1 | 4h | 100%
Allow teacher to submit the profile for reviewing by admins | Trần Quốc Việt | 1 | 8h | 100%
Show teacher's reviews in their profile | Lương Duy Hưng | 0 | 10h | 100%
Show feedbacks from students privately | Nguyễn Quý Hải | 0.5 | 12h | 100%
Recommend suitable teachers to students | Lương Quang Khánh | 0.75 | 32h | 100%
Search for teachers based on subject, teachers’ location, suitable teaching date, level (fundamental, advanced, …) | Nguyễn Quý Hải | 1 | 28h | 100%
Can leave ratings & reviews after learning | Trần Quốc Việt | 1 | 16h | 100%
Can leave feedback to teachers (anonimity is optional) | Trần Quốc Việt | 1 | 16h | 100%
Chatbox | Lương Quang Khánh | 0.82999999999999996 | 80h | 100%
Voice/Video call | Lương Duy Hưng | 1 | 80h | 100%
Phone number (basic contact method) | Nguyễn Quý Hải | 1 | 8h | 100%
Integrate with payment methods | Trần Quốc Việt | 1 | 24h | 100%
Build customer service DB | Lương Quang Khánh | 1 | 16h | 100%
Answer support message | Nguyễn Quý Hải | 0 | 16h | 100%
Answer hotline calls (aka. Urgent contact) | Nguyễn Quý Hải | 1 | 8h | 100%
Allow tracking of chat messages | Trần Quốc Việt | 0 | 12h | 100%
Allow tracking of reviews | Nguyễn Quý Hải | 0 | 24h | 100%
Allow tracking of feedbacks | Nguyễn Quý Hải | 0.82999999999999996 | 24h | 100%
Allow manual user banning | Trần Quốc Việt | 1 | 12h | 100%
Allow to approve/deny teachers' profiles | Trần Quốc Việt | 1 | 6h | 100%
User testing | Lương Duy Hưng | 0 | 24h | 100%
Smoke testing | Nguyễn Quý Hải | 0 | 8h | 100%
System testing | Trần Quốc Việt | 0 | 40h | 100%
Stress test | Lương Quang Khánh | 0 | 24h | 100%